## Sheet1
# | Reported Date | Reported By | Severity | Status | Assigned To | Short Description | Expected Results | Actual Results | Steps to reproduce
1 | 2024-10-13 | Wendy | P4: annoying or limiting, but could be shipped as-is | resolved | Wendy | If the player runs into a solid object. The player will not be able to move in the initial direction of movement (even if solid object is no longer in the way) unless they first move in the opposite direction. - Update: bug changed to player being able to move through objects if changing between two movement keys (eg. up/left). Fix for previous bug caused this one. | 1. Player moves left 2. Player moves up or down 3. Player moves left if no solid object is in the way | 1. Player moves left 2. Player moves up or down 3. Player does not move left (even if no solid object is in the way) | Bug occurs in all directions of movement. Below steps cover moving left as an example. 1. Press left key is move left into a solid object (furniture/table) 2. Press up or down key until player is clear of solid object 3. Press left key to try move player to the left
2 | 2024-10-14 | Aayush | P4: annoying or limiting, but could be shipped as-is | resolved | Aayush | Enemy sprites sometimes get rendered close to the walls and get stuck there, instead of moving towards the player. They get stuck in the walls and can only move along the walls, if at all. | The sprites move towards the player. | Sprites get stuck in walls sometimes | The bug occurs at random depending upon the enemy sprite's spawn location. It happens at least once every few games.
3 | 2024-10-14 | Aayush | P5: minor or feature that nice to have but could ship in future release | resolved | Luke | Dash only happens in one direction (to the right). | The player should dash in the direction of movement (if any) else in a default direction. | Dash only in the right direction. | Press Space to dash while moving.
4 | 2024-10-14 | Aayush | P4: annoying or limiting, but could be shipped as-is | resolved | Luke | Dash causes the player to stop once the dash action is complete. The player needs to re-press the directional key to continue the movement. | Player continues to move in the direction of the currently pressed arrow keys. | Player stops after the dash is complete, even though a directional key is still pressed. | Press Space to dash while moving.
5 | 2024-11-03 | Luke | P5: minor or feature that nice to have but could ship in future release | open | Luke | Player is able to dash past and inside of walls | Player should collide with and stop before once reaching the wall after a dash. | Player dashes to the position, ignoring all obstacles. | Press Space to dash while facing a wall.
6 | 2024-11-03 | Luke | P5: minor or feature that nice to have but could ship in future release | open | Luke | Knocking back an enemy with an attack results in them getting stuck in place. | After being knocked back, the enemy should continue pathing towards the player. | After being knocked back, the enemy moves towards the location where it was hit and gets stuck. In some cases, it simply stops moving. | 1. Press P to enter debug mode. 2. Left click to attack an enemy. 3. Move away from the enemy.
7 | 2024-11-03 | Logan | P5: minor or feature that nice to have but could ship in future release | in-progress | Logan | UI stays bright when game is paused | UI should darken to the same factor as the rest of the screen | UI stays same brightness throughout the game | Press ESC key to pause game
8 | 2024-11-03 | Logan | P4: annoying or limiting, but could be shipped as-is | in-progress | Logan | Player gets stuck while dragging along wall in the vertical direction | Player should be able to walk up against walls without getting stuck | Player sometimes gets stuck on the walls and stays overlapped with wall tile | Press one key (left or right) going into a side wall and one key either up or down. Drag player along walls for at most ten seconds and the player will get stuck, even when keys are released.